## Agile Estimates
Modules | Requirements | Value Points | User Story Points | Bang for the buck | Status
Application Monitoring | Signatory should be able to accept an application | 13 | 1 | 13 | OK | Code | Sprint | Status
Application Monitoring | Signatory should be able to reject an application | 13 | 1 | 13 | OK |  | 1st | Failed
Application Monitoring | Admin should be able to accept applications. | 13 | 1 | 13 | OK |  | 2nd | Success
Application Monitoring | Admin should be able to reject applications. | 13 | 1 | 13 | OK |  | 3rd | Success
Scholarship Management | Admin should be able to delete scholarship | 8 | 1 | 8 | OK |  | 4th | So-So
Scholarship Management | Admin should be able to add scholarships. | 8 | 1 | 8 | OK |  | 5th | So-So
Application Monitoring | Student should be able to apply for a scholarship | 21 | 3 | 7 | OK
Application Monitoring | Signatory should be able to return and forward an application | 13 | 5 | 2.6 | OK
Account Management | User should be able to login. | 2 | 1 | 2 | OK
Application Monitoring | Student should be able to view his scholarship status | 13 | 8 | 1.625 | OK
Application Monitoring | Signatory should be able to monitor applications | 13 | 8 | 1.625 | OK
Application Monitoring | Admin should be able to monitor applications | 13 | 8 | 1.625 | OK
Scholarship Management | Admin should be able to edit scholarship | 8 | 5 | 1.6
Scholarship Management | Admin should be able to define signatory | 5 | 5 | 1 | OK
Account Management | Admin should be able to add user account | 1 | 1 | 1 | OK
Account Management | Admin should be able to delete user account | 1 | 1 | 1
Scholar Monitoring | Student should be able to submit Accomplishments Reports | 1 | 2 | 0.5 | OK
Scholar Monitoring | Student should be able to submit Financial Reports | 1 | 2 | 0.5 | OK
Scholar Monitoring | Admin should be able to review Accomplishments Reports | 1 | 2 | 0.5 | OK
Scholar Monitoring | Admin should be able to review Financial Reports. | 1 | 2 | 0.5 | OK
Scholarship Management | Admin should be able view available requirements | 3 | 8 | 0.375
Account Management | Admin should be able to edit user account | 1 | 5 | 0.2
Account Management | Student should be able to edit profile | 1 | 5 | 0.2 | OK
Application Monitoring