## Agile Estimates
Modules | Requirements | Value Points | User Story Points | Bang for the buck
Application Monitoring | Signatory should be able to accept an application | 13 | 1 | 13
Application Monitoring | Signatory should be able to reject an application | 13 | 1 | 13 | Label
Application Monitoring | Admin should be able to accept applications. | 13 | 1 | 13 |  | 1st
Application Monitoring | Admin should be able to reject applications. | 13 | 1 | 13 |  | 2nd
Scholarship Management | Admin should be able to delete scholarship | 8 | 1 | 8 |  | 3rd
Scholarship Management | Admin should be able to add scholarships. | 8 | 1 | 8 |  | 4th
Application Monitoring | Student should be able to apply for a scholarship | 21 | 3 | 7 |  | 5th
Application Monitoring | Signatory should be able to return and forward an application | 13 | 5 | 2.6
Account Management | User should be able to login. | 2 | 1 | 2
Application Monitoring | Student should be able to view his scholarship status | 13 | 8 | 1.625
Application Monitoring | Signatory should be able to monitor applications | 13 | 8 | 1.625 |  | User Acceptable Criteria
Application Monitoring | Admin should be able to monitor applications | 13 | 8 | 1.625 | Sprint 1 | System should be able to add an applcation to scholarship (See database for output)
Scholarship Management | Admin should be able to edit scholarship | 8 | 5 | 1.6 | Sprint 2 | System should post accept or reject status (See database)
Scholarship Management | Admin should be able to define signatory | 5 | 5 | 1 | Sprint 3 | System should post accept or reject status (See database)
Account Management | Admin should be able to add user account | 1 | 1 | 1 | Sprint 4 | Test Scorecard
Account Management | Admin should be able to delete user account | 1 | 1 | 1
Scholar Monitoring | Student should be able to submit Accomplishments Reports | 1 | 2 | 0.5
Scholar Monitoring | Student should be able to submit Financial Reports | 1 | 2 | 0.5
Scholar Monitoring | Admin should be able to review Accomplishments Reports | 1 | 2 | 0.5
Scholar Monitoring | Admin should be able to review Financial Reports. | 1 | 2 | 0.5
Scholarship Management | Admin should be able view available requirements | 3 | 8 | 0.375
Account Management | Admin should be able to edit user account | 1 | 5 | 0.2
Account Management | Student should be able to edit profile | 1 | 5 | 0.2
Application Monitoring